VIGIL

Implementation Roadmap

Derived from Section 7 of the Market Comparison Report

Plan horizon: May 2026 → Q2 2027

# Executive Summary

This roadmap operationalises the five investment priorities identified in §7 of the VIGIL Market Comparison Report. The first three priorities (notifier suite, Redis/Elasticsearch connectors, statistical anomaly detection) are engineering items deliverable in Q2 2026 with a small team. Priority 4 (OTel trace-to-query correlation) is a Q3 2026 data-plane item. Priority 5 (SCIM + SOC 2 Type II) is a Q3–Q4 track that is partly engineering and partly organisational.

The sequencing is deliberate: items 1–3 remove the three most cited reasons prospects walk away in competitive evaluations, and each one is small enough to ship independently. Item 4 unlocks the "Datadog-style full-stack correlation" story without a full APM rewrite. Item 5 unblocks enterprise RFPs above roughly 500 seats.

Assumed team size for this roadmap: two backend engineers, one frontend engineer, one SRE/security engineer shared across tracks, and one product manager. Dates assume kick-off on 05 May 2026.

# 1. Roadmap at a Glance

The table below is the commitment view: what we are shipping, when we start, when it leaves QA, and who owns it. Everything downstream in this document is a detailed breakdown of these rows.

| Priority | Workstream | Tier | Start | Ship | Owner |
| --- | --- | --- | --- | --- | --- |
| P1 | Notifier suite (PagerDuty / Opsgenie / Teams / signed webhook) | Pro+ | W1 (05 May 26) | W4 (29 May 26) | Backend #1 |
| P2 | Redis + Elasticsearch connectors | Pro+ | W1 (05 May 26) | W6 (12 Jun 26) | Backend #2 |
| P3 | Statistical anomaly detection in alertService | Enterprise | W5 (02 Jun 26) | W8 (26 Jun 26) | Backend #1 |
| P4 | OTel trace → per-query view correlation | Pro+ | W10 (10 Jul 26) | W18 (04 Sep 26) | Backend #1+FE |
| P5a | SCIM 2.0 user provisioning | Enterprise | W14 (07 Aug 26) | W20 (18 Sep 26) | SRE/Security |
| P5b | SOC 2 Type II observation window | Enterprise | W20 (18 Sep 26) | W48 (02 Apr 27) | SRE/Security + ext. auditor |

Workstreams P1 and P2 run in parallel from week 1 because they do not share code paths. P3 picks up when P1 is done (same owner). P4 starts after the Pro-tier capacity work (P1, P2) so the frontend team can focus on UI. P5a and P5b are sequenced so SCIM ships before the SOC 2 window locks scope.

# 2. P1 — Notifier Suite

The single highest-leverage gap. Every competitor ships PagerDuty and Opsgenie integrations; buyers in regulated industries additionally ask for Teams and signed webhooks. Closing this closes the largest single reason VIGIL loses SRE-led evaluations.

## 2.1 Scope

- PagerDuty Events API v2 notifier with trigger and resolve actions and dedup_key on the alert id.

- Opsgenie notifier using GenieKey auth, P1–P5 priority mapping, and optional team responder.

- Microsoft Teams notifier using the MessageCard format with severity-coloured facts.

- Generic signed-webhook notifier with HMAC-SHA256 signature header (X-VIGIL-Signature: t=TS,v1=HEX) and a receiver-side verifier helper.

- NotifierManager: parallel fan-out, per-alert-id dedupe window, exponential-backoff retry, severity filter.

- Admin UI: add / test / rotate secrets for each notifier destination.

## 2.2 Acceptance criteria

- End-to-end: raising a critical alert in staging fires a PagerDuty incident, an Opsgenie alert, a Teams card, and a signed webhook within five seconds.

- Dedupe: firing the same alert twice within the configured window produces one downstream page, not two.

- Retry: a flaky 5xx from the destination triggers exponential retry with capped attempts and surfaces a visible delivery failure in the admin UI.

- Unit coverage on notifier code ≥ 80 % lines / 70 % branches; all notifiers isolated from live HTTP in tests via an HttpFn seam.

## 2.3 Effort & risks

Effort: ~4 engineer-weeks (1 backend engineer, overlapping 0.5 FE for admin screens). Risks: PagerDuty and Opsgenie rate-limit behaviour during incident storms; mitigate with per-destination queue and back-pressure surface. Low integration risk — all four destinations are additive, not replacing existing code paths.

# 3. P2 — Redis and Elasticsearch Connectors

Redis is the most common cache tier in production workloads; Elasticsearch is the most common search/log tier. Covering both brings VIGIL’s engine breadth to par with Datadog and SolarWinds DPM and is the prerequisite for marketing VIGIL as a "full data-tier" observer.

## 3.1 Scope

- RedisConnector (ioredis) with INFO-based overview, SLOWLOG GET for top-N slow commands, LATENCY LATEST with graceful fallback, keyspace statistics, and connected-clients trend.

- ElasticsearchConnector (@elastic/elasticsearch) with cluster health, indices stats, node stats, hot-threads sampling, and pending tasks.

- Common adapter pattern extending BaseAdapter so both appear in the same UI treatment as PG/MySQL/Mongo/MSSQL/Oracle.

- Optional peer-dependency loading so the core SDK does not bloat for customers who do not use these engines.

- Frontend views under components/views/redis and components/views/elasticsearch mirroring the existing mongodb / mysql views.

## 3.2 Acceptance criteria

- Connection test from admin UI succeeds against both an authenticated Redis 7 cluster and an Elasticsearch 8 cluster over TLS.

- Default overview panels render with sample data within 2 s of connection open.

- Slowlog / hot-threads surfaces are paginated and search-filterable.

- Adapter-level unit tests use fake loaders so CI does not require running Redis or Elasticsearch.

## 3.3 Effort & risks

Effort: ~6 engineer-weeks (1 backend + 0.5 FE). Risks: Elasticsearch’s licensing split (Elastic vs OpenSearch) means the connector must be compatible with both wire protocols; plan on testing against OpenSearch 2.x as well. Redis Cluster mode introduces topology discovery; ship single-primary first and cluster as a fast follow.

# 4. P3 — Statistical Anomaly Detection

Rule-based thresholds require a human to know the right number. Competitors now ship baseline-aware anomaly detectors. This priority wires three complementary detectors into the existing alertService so customers can set a detector type on any metric instead of a static threshold.

## 4.1 Scope

- RollingZScoreDetector with a circular buffer and Welford’s online algorithm for O(1) mean/variance updates.

- EwmaDetector (exponentially-weighted moving average) with configurable alpha and O(1) memory — cheap, deploy everywhere.

- MadDetector (median absolute deviation with 0.6745 scaling) — robust to outliers; returns neutral score when MAD collapses to 0.

- Detector registry wired into alertService.evaluate() behind a new alert rule type.

- Admin UI: select detector, preview baseline on historical data for the selected metric, commit.

## 4.2 Acceptance criteria

- Synthetic workload with a known injected spike produces an alert within one evaluation cycle on all three detectors.

- Stable workload with diurnal seasonality produces zero alerts over a 48-hour backtest.

- Evaluation cost ≤ 1 ms per detector per metric at the 1 M-points-per-minute rate on a single alert worker.

- Test suite covers degenerate cases (empty window, constant series, single outlier, heavy-tailed series).

## 4.3 Effort & risks

Effort: ~3 engineer-weeks. Risks: false-positive fatigue — mitigate by shipping detectors in "suggest" mode first so customers can review suggested anomalies before they page. Documentation matters: publish a short guide on when to pick z-score vs. EWMA vs. MAD.

# 5. P4 — OTel Trace-to-Query Correlation

OpenTelemetry ingest is already in place. The value is unlocked when a user clicks through from an app trace to the exact DB query that was the slow span. This is the primary observability gap against Datadog DBM and Dynatrace.

## 5.1 Scope

- Ingest-time join: tag each incoming query row with the active trace_id / span_id if one is present on the connection context (supported for PG / MySQL / MSSQL via SET application_name or session comment patterns).

- Storage: add trace_id and span_id columns to the query_events table; index on trace_id.

- API: /api/traces/:traceId/queries returns every query observed for a trace, with latency contribution and plan hash.

- Frontend: new Trace Detail view with a timeline of spans and an inline "drill into query" panel that reuses the existing per-query view component.

- Backwards-compat: existing per-query view keeps working for customers who do not emit OTel.

## 5.2 Acceptance criteria

- Demo app instrumented with @opentelemetry/api produces a trace whose DB span resolves to one query row in the Trace Detail view.

- 95th-percentile join latency < 200 ms end-to-end under the benchmark workload.

- Documentation: a 1-page "instrument your app" guide for each of Node, Python, Java, and Go.

## 5.3 Effort & risks

Effort: ~8 engineer-weeks split across one backend engineer and the frontend engineer. Risks: the join only works if the app actually propagates trace context to the DB driver — most do not by default. Expect support burden for customers who cannot see their trace_ids; mitigate with a diagnostic endpoint that echoes whatever context the connector saw.

# 6. P5 — SCIM Provisioning and SOC 2 Type II

These two items unblock enterprise RFPs above the mid-market ceiling. SCIM is the engineering half; SOC 2 Type II is the organisational half. They share an owner because both are security-adjacent and because SOC 2 observation has to start after major access-control code changes have landed.

## 6.1 P5a — SCIM 2.0

- SCIM endpoints: /scim/v2/Users, /scim/v2/Groups, /scim/v2/ServiceProviderConfig, /scim/v2/ResourceTypes, /scim/v2/Schemas.

- Filter parser for SCIM filter expressions (eq, ne, co, sw, ew, pr, gt, lt) with allow-listed attributes.

- Tenant-scoped bearer-token auth separate from the dashboard session token.

- Okta and Entra ID (Azure AD) as the two reference IdPs for integration testing.

- Acceptance: provisioning and de-provisioning a user via Okta reflects in VIGIL within 30 s; role assignment via SCIM groups maps to existing VIGIL RBAC roles.

- Effort: ~6 engineer-weeks (1 backend + security review).

## 6.2 P5b — SOC 2 Type II

- Type I readiness audit (gap assessment) in W20–W24.

- Controls to implement before the observation window opens: change-management policy, vendor risk register, access-review cadence, incident-response runbook, encryption-at-rest verification, tamper-evident audit log.

- Observation window: 6 months, W24 → W48 (late September 2026 → early April 2027).

- Type II report delivered in Q2 2027.

- Effort: ~0.25 FTE sustained for the SRE/Security engineer across the observation window, plus external auditor spend.

# 7. Cross-Cutting Concerns

## 7.1 Testing and CI

Every priority above lands with Vitest unit coverage ≥ 70 % lines. Any notifier or connector that touches a third-party service is tested via an injected HttpFn / fake loader seam so CI does not require network access. Integration tests run nightly against ephemeral containers (Redis, Elasticsearch, MSSQL, Mongo).

## 7.2 Documentation

Each shipped item comes with a short (1–2 page) "how to set up" guide linked directly from the admin UI. The guides are more important than the code for adoption — customers will not turn on features they cannot see documented. Target: every guide reviewed by a customer-success engineer before merge.

## 7.3 Go-to-market

Marketing should sequence launch posts roughly one week after each ship date: PagerDuty/Opsgenie integration landing page, "VIGIL now monitors Redis" blog + changelog, "Anomaly detection without rules" blog, "Trace-to-query in one click" case study. SCIM and SOC 2 are sales-enablement assets — the RFP-response library should be updated the same week the capabilities ship.

## 7.4 Feature flags

Every new capability ships behind a featureGate entry so it can be rolled out tier-by-tier without code changes. Community tier gets Redis + Elasticsearch at GA; anomaly detection, SCIM, trace correlation remain Enterprise-tier features.

# 8. Risk Register

| ID | Risk | Likelihood | Mitigation |
| --- | --- | --- | --- |
| R1 | PagerDuty rate-limits during an incident storm, delaying pages | Medium | Per-destination queue + back-pressure surfaced in admin UI |
| R2 | Elastic vs OpenSearch wire-protocol drift breaks the connector | Medium | CI runs against both; document support matrix; ship Elastic first, OpenSearch fast-follow |
| R3 | Anomaly detectors produce false-positive alert fatigue | High | Ship in "suggest" mode first; require a 48-hour backtest preview in UI before activation |
| R4 | OTel context does not reach the DB driver for most customer apps | High | Publish per-language instrumentation guides; add a diagnostic endpoint that echoes observed context |
| R5 | SOC 2 observation window extended by late control failure | Medium | Run Type I readiness audit before W24; track controls in a weekly security standup |
| R6 | SCIM integration certification delays (Okta/Entra) | Low | Kick off the Okta integration submission as soon as /Users CRUD is functional, in parallel with /Groups work |
| R7 | Scope creep on Trace Detail UI eats the P4 budget | Medium | Hard cap the first release to timeline + drill-to-query; explicit "next quarter" list for anything else |

# 9. Success Metrics

Every priority in this roadmap has an outcome metric, not just an output metric. "Shipped" is not the target; "shipped AND changed buyer behaviour OR reduced customer pain" is. The table below states the commitment explicitly.

| Priority | Success metric | Target | Measured via |
| --- | --- | --- | --- |
| P1 | Alerts delivered to external incident tool within SLA | 99.5 % of fires within 5 s | alertService delivery telemetry |
| P1 | Deals lost due to "no PagerDuty" drop | → zero by end Q3 2026 | Sales CRM won/lost reasons |
| P2 | Customers with at least one Redis or Elasticsearch connection | ≥ 20 % of active accounts | Usage analytics |
| P3 | Paging noise reduction in anomaly customers | ≥ 30 % fewer pages / week | Before/after comparison on opt-in accounts |
| P4 | Trace-to-query click-through rate | ≥ 40 % of trace-detail views | Product analytics |
| P5a | Enterprise customers provisioning users via SCIM | ≥ 50 % by Q1 2027 | Tenant-level SCIM audit log |
| P5b | SOC 2 Type II report issued | Q2 2027 | External auditor deliverable |

# 10. Governance & Cadence

- Weekly engineering standup against the roadmap; slippage > 1 week triggers a re-plan for the downstream row.

- Bi-weekly steering review with engineering lead, product, and sales — the only forum that can change roadmap order.

- Ship gate: a roadmap row moves from "ship" to "launched" only when acceptance criteria, docs, admin UI, and the related marketing asset are all merged.

- Customer beta: every priority goes to 3–5 friendly customers for a one-week beta before GA; beta feedback is merged before announcement.

- Post-launch review: 30 days after launch, revisit the success metric for the priority and decide whether follow-up investment is warranted.